## Sheet1
Project | Scheduled Completion | Responsible | Report Date | Status
Emory Asbury Water lines | 2015-01-30 | Carter & Sloope | 2013-12-06 | Bid has been awarded, contracts being prepared, preconstruction conference scheduled for Dec 18; will prepare a letter to residents soon.
|  |  | 2013-12-18 | Preconstruction conference held. Project start date is January 6.
|  |  | 2013-12-19 | Letters mailed to all residents affected on Emory and Asbury.
|  |  | 2013-12-31 | David Strickland working on easement with school board that will help with free boring to install line in front of Palmer Stone School.
LMIG street resurfacing | 2014-04-15 | Jody | 2013-12-06 | Preparing new estimates for CC meeting on Dec 16.
|  |  | 2013-12-19 | Council selected W. Soule - project application mailed to DOT; total $36,100.
|  |  | 2013-12-31 | We will prepare RFP and issue it in February.
Surplus Property | 2013-12-16 | Lauran | 2013-12-06 | Bids will be received Dec 10 and opened Dec 16.
|  |  | 2013-12-06 | We have had a phone call from Porterdale expressing interest.
|  |  | 2013-12-16 | Council awarded bid for garbage truck to Porterdale and bid for Crown Vic to Latham Sanitation
|  |  | 2013-12-31 | Both vehicles transferred, PROJECT COMPLETE
Fees | 2013-12-16 | Lauran | 2013-12-06 | A revised list of city fees will be ready for the work session.
|  |  | 2013-12-16 | Fee list presented and reviewed at work session. PROJECT COMPLETE
Update flood zone ordinance | 2014-02-01 | Bob | 2013-12-06 | FEMA has issued a new flood map and we may need to update our ordinances before March, 2014.
|  |  | 2013-12-31 | This will be discussed at the January work session.
Prepare an ordinance regulating solar panels | 2014-01-10 | Bob | 2013-12-06 | We have samples from ECG (Electric Cities of Georgia).
Develop an investment strategy | 2014-01-10 | Bob & Lauran | 2013-12-06 | CD's and checking accounts may not be the best place to invest our funds. We will look at alternatives.
Draft an ordinance to prohibit cutting down trees on city property | 2014-01-10 | Bob & David | 2013-12-06 | This was requested at the council retreat.
|  |  | 2013-12-09 | Asked David to prepare a draft ordinance.
|  |  | 2013-12-10 | Draft ordinance received. Will be on work sesson agenda for January.
Get bids on engineering services | 2014-01-10 | Bob | 2013-12-06 | We have one proposal and we will solicit several more.
|  |  | 2013-12-31 | Our goal is to have them ready to be discussed at the January work session.
Install emergency generators at city hall and the barn | 2014-01-10 | Bob & Jody | 2013-12-06 | Jody is going to work with an electrician so we can prepare the bids.
Renew contract with Connie Head, city arborist | 2014-01-05 | Bob | 2013-12-06 | It's an annual contract that automatically renews; we just need to update the budget amounts.
|  |  | 2013-12-31 | Contract signed by Mayor and Connie Head. PROJECT COMPLETE
Determine who is 100' from a sewer line and how to enforce ordinance | 2014-01-10 | Bob, Lauran, & Jody | 2013-12-06 | We will have a report to Council for the January work session.
Evaluate Oxford North neighborhood as location for sewer system expansion | 2014-03-01 | Bob & Jody | 2013-12-30 | Jody will review maps and terrain before we consider hiring an engineer for a preliminary design.
Report to council on our water billings | 2013-12-16 | Bob & Lauran | 2013-12-06 | We met with Bobby Snipes of Newton County Water 12/3/13 to review the seven meters that deliver water to the city and how we are billed for them.
|  |  | 2013-12-31 | Will include report on agenda for January work session.
Install 175th birthday banners | 2014-01-15 | Jody | 2013-12-06 | Emory has ordered the banners; Jody has ordered the mounting hardware.
|  |  | 2013-12-17 | We have received the mounting brackets
|  |  | 2013-12-31 | Banners received. Jody, Bob, and Mayor Roseberry reviewed locations for banners.
Whatcoat Street improvements | 2014-12-31 | Bob | 2013-12-13 | Waiting on report from Newton Center before making any design decisions.
|  |  | 2013-12-19 | Met with Adam Kirk at Newton Center. They are working on project but somewhat delayed by Kay Lee's knee surgery.
New agreement with Newton Trails | 2014-03-01 | Bob | 2013-12-06 | Received draft agreement from Newton Trails.
|  |  | 2013-12-31 | Made several changes. Sent to David Strickland for review. He's OK with it. Sent revised version to Newton Trails and invited them to January 21 work session for further discussion.
Update financial policies | 2014-03-03 | Bob | 2013-12-20 | Making changes from December council work session.
|  |  | 2014-01-06 | Submitted for first reading approval.